## Sprint Burn Down Chart
Sprint | Day/Date | Expected Time | Actual Time | Story | Story Point | Task ID | Task | Estimated Time |  | Total Story Point | Total Estimated Time
1((23/8/16)) | 0 | 26.5 | 26.5 | Story01:Customer Testimony |  | T01 | Create a Customer Testimony Page | 3 | 2016-09-03 |  | 26.5 | 1.8929
| 1 | 24.6071 | 26.5 |  |  | T02 | Write test cases | 2
| 2 | 22.7143 | 26.5 |  |  | T03 | Create link on main page | 2
| 3 | 20.8214 | 26.5 |  |  | T04 | Verify story is complete | 1
| 4 | 18.9286 | 26.5 | Story 02: Simple Faq |  | T01 | Establish FAQ Page | 3 | 2016-09-05
| 5 | 17.0357 | 26.5 |  |  | T02 | Write test cases | 1
| 6 | 15.1429 | 26.5 |  |  | T03 | verify story completion | 1
(30/8/16) | 7 | 13.25 | 26.5 | Story 04: Customer Feedback |  | T01 | Create a Customer Feedback Page | 3 | 2016-09-03
| 8 | 11.3571 | 26.5 |  |  | T02 | Write test cases | 2
| 9 | 9.4643 | 25.5 |  |  | T03 | Verify story is complete | 1
| 10 | 7.5714 | 25.5 | Story 05: Terms & Conditions |  | T01 | Establish Terms & Conditions Page | 3 | 2016-09-04
| 11 | 5.6786 | 19.5 |  |  | T02 | Write test cases | 1
| 12 | 3.7857 | 16.5 |  |  | T03 | Link Terms & Conditions to Homepage | 1
| 13 | 1.8929 | 13.5 | Story 22: Manager/Employee Login Portal |  | T01 | Create Login Page | 1 | 2016-09-01
(6/9/16) | 14 | 0 | 13.5 |  |  | T02 | Write acceptance Tests (Username & Password) | 1
[6 empty] | T03 | Verify story is complete | 0.5