## Sheet1
Date | Days | Expected(Hours) | Real (Hours) | Task/Story ID | Project | Expected (Hours) | Real (Hours) | Date Complete
2016-09-20 | 1 | 115 | 115 | Story 03 | Update Company News
2016-09-21 | 2 | 109.25 | 115 | T01 | Create News Database | 1 | 1 | 2016-10-02
2016-09-22 | 3 | 103.5 | 115 | T02 | Customer Site Webpage Design | 2
2016-09-23 | 4 | 97.75 | 115 | T03 | Customer site function implementation | 3 | 1 | 2016-10-02
2016-09-24 | 5 | 92 | 115 | T04 | Customer site test case | 2
2016-09-25 | 6 | 86.25 | 115 | T05 | Manager site Webpage design | 2
2016-09-26 | 7 | 80.5 | 109 | T06 | Manager site function implementation | 4 | 2 | 2016-10-02
2016-09-27 | 8 | 74.75 | 109 | T07 | Manager site test case. | 3
2016-09-28 | 9 | 69 | 109 | T08 | Files upload function(16)
2016-09-29 | 10 | 63.25 | 101 | Story 11 | Reporting
2016-09-30 | 11 | 57.5 | 101 | T01 | Align Delivery information | 2
2016-10-01 | 12 | 51.75 | 101 | T02 | Include PDF Printable report | 3
2016-10-02 | 13 | 46 | 93 | T03 | Verify the tasks | 1
2016-10-03 | 14 | 40.25 | 93 | Story | Permission Management
2016-10-04 | 15 | 34.5 | 86 | T01 | Create customer login page | 3 | 1 | 2016-09-26
2016-10-05 | 16 | 28.75 |  | T02 | Allow only managers to edit/delete | 3 | 1 | 2016-09-26
2016-10-06 | 17 | 23 |  | T03 | Verify tasks | 1
2016-10-07 | 18 | 17.25 |  | Story 12 | Customer Information
2016-10-08 | 19 | 11.5 |  | T01 | Create Customer Login Page | 3
2016-10-09 | 20 | 5.75 |  | T02 | Create Separate Page for Package Quote | 3
2016-10-10 | 21 | 0 |  | Story 19 | Receive Accurate Tracking Quotes
2016-10-11 | End |  |  | T01 | Create Separate Page for Calculations | 4 | 3 | 2016-09-29
|  |  |  | T02 | Create shipping quote calculator | 3 | 2 | 2016-09-29
|  |  |  | T03 | Verify story is complete | 1 | 1 | 2016-09-29
|  |  |  | Story | Track Employee
|  |  |  | T01 | Implement Delivery Status Table | 1 | 1 | 2016-10-04
|  |  |  | T02 | Employee Interface Design | 6
|  |  |  | T03 | Manager Interface Implementation | 6 | 2 | 2016-10-04
|  |  |  | T04 | Customer Interface Implementation | 4
|  |  |  | T05 | Employee function implementation | 16
|  |  |  | T06 | Manager function implementation | 24
|  |  |  | T07 | Customer function implementation | 4
|  |  |  | T08 | Manager site test case | 3
|  |  |  | T09 | Employee Test Case | 5
|  |  |  | T10 | Customer Test Case | 2
[5 empty] | Total Expected Hours | 115
[5 empty] | Average Expected Hours | 5.75