## Sheet1
Date | Days | Expected(Hours) | Real (Hours) | Task/Story ID | Project | Expected (Hours) | Real (Hours) | Date Complete
2016-09-20 | 1 | 99 | 99 | Story 03 | Update Company News
2016-09-21 | 2 | 94.05 | 99 | T01 | Create News Database | 1 | 1 | 2016-10-02
2016-09-22 | 3 | 89.1 | 99 | T02 | Customer Site Webpage Design | 2 | 1 | 2016-10-05
2016-09-23 | 4 | 84.15 | 99 | T03 | Customer site function implementation | 3 | 1 | 2016-10-02
2016-09-24 | 5 | 79.2 | 98 | T04 | Customer site test case | 2 | 2 | 2016-10-04
2016-09-25 | 6 | 74.25 | 98 | T05 | Manager site Webpage design | 2 | 2 | 2016-10-05
2016-09-26 | 7 | 69.3 | 92 | T06 | Manager site function implementation | 4 | 2 | 2016-10-02
2016-09-27 | 8 | 64.35 | 92 | T07 | Manager site test case. | 3 | 2 | 2016-10-04
2016-09-28 | 9 | 59.4 | 92
2016-09-29 | 10 | 54.45 | 84 | Story | Permission Management
2016-09-30 | 11 | 49.5 | 84 | T01 | Create customer login page | 3 | 1 | 2016-09-26
2016-10-01 | 12 | 44.55 | 84 | T02 | Allow only managers to edit/delete | 3 | 1 | 2016-09-26
2016-10-02 | 13 | 39.6 | 76 | T03 | Verify tasks | 1 | 1 | 2016-09-24
2016-10-03 | 14 | 34.65 | 76 | Story 12 | Customer Information
2016-10-04 | 15 | 29.7 | 64 | T01 | Create Customer Login Page | 3 | 3 | 2016-10-10
2016-10-05 | 16 | 24.75 | 60 | T02 | Create Separate Page for Package Quote | 3 | 1 | 2016-10-10
2016-10-06 | 17 | 19.8 | 60 | Story 19 | Receive Accurate Tracking Quotes
2016-10-07 | 18 | 14.85 | 60 | T01 | Create Separate Page for Calculations | 4 | 3 | 2016-09-29
2016-10-08 | 19 | 9.9 | 60 | T02 | Create shipping quote calculator | 3 | 2 | 2016-09-29
2016-10-09 | 20 | 4.95 | 36 | T03 | Verify story is complete | 1 | 1 | 2016-09-29
2016-10-10 | 21 | 0 | 14 | Story | Track Employee
2016-10-11 | End |  |  | T01 | Implement Delivery Status Table | 1 | 1 | 2016-10-04
|  |  |  | T02 | Employee Interface Design | 6
|  |  |  | T03 | Manager Interface Implementation | 6 | 2 | 2016-10-04
|  |  |  | T05 | Employee function implementation | 16 | 3 | 2016-10-10
|  |  |  | T06 | Manager function implementation | 24 | 12 | 2016-10-09
|  |  |  | T08 | Manager site test case | 3
|  |  |  | T09 | Employee Test Case | 5
[5 empty] | Total Expected Hours | 99
[5 empty] | Average Expected Hours | 4.95